## Task Board
# | Task | Status | Domain | Owner | Priority | Course | Start | End | Start Now?
WS1-1 | Project spec document (v1-v3) | Done |  | Steven | Medium | Shared | 2026-02-24 | 2026-03-07
WS1-2 | Database schema design (9 tables) | Done |  | Steven | Medium | Shared | 2026-03-01 | 2026-03-07
WS1-3 | Proof of Concept prototype | Done |  | Steven | Medium | AI Course | 2026-03-03 | 2026-03-09
WS1-4 | Scrape 56 DHRM pages | Done |  | Steven | High | Big Data | 2026-03-10 | 2026-03-15
WS1-5 | Parse HTML (50 groups) | Done |  | Steven | High | Big Data | 2026-03-12 | 2026-03-18
WS1-6 | Parse PDF (6 groups, 3 variants) | Done |  | Steven | High | Big Data | 2026-03-16 | 2026-03-24
WS1-7 | Classification prompt v1 | Done |  | Steven | Medium | Shared | 2026-03-20 | 2026-03-24
WS1-8 | Data validation (56 groups, 294 roles) | Done |  | Steven | High | Big Data | 2026-03-22 | 2026-03-24
WS1-9 | FY26 salary + W&M grades + crosswalk | Done |  | Steven | High | Shared | 2026-03-23 | 2026-03-25
WS1-10 | DB load + Excel export | Done |  | Steven | High | Big Data | 2026-03-25 | 2026-03-26
WS1-11 | Client response received (Mar 27) | Done |  |  | High | Shared | 2026-03-27 | 2026-03-27
A1 | Environment setup (conda griffin) | Done | Technical | Steven | High | Shared | 2026-03-30 | 2026-03-30
A2 | Workday scrape (CQM orchestrated) | Done | Technical | Steven | High | Big Data | 2026-03-30 | 2026-03-31
A3 | Label stripping + censored PDs | Done | Technical | Steven | High | Shared | 2026-03-31 | 2026-03-31
DOC | Project docs created (kanban, Gantt, briefing, etc.) | Done |  | Steven | Medium | Shared | 2026-03-30 | 2026-03-31
DOC | Team brief PowerPoint (15 slides) | Done |  | Steven | Medium | Shared | 2026-03-31 | 2026-03-31
DOC | Professor email drafted (NOT sent) | Done |  | Steven | Medium | Shared | 2026-03-30 | 2026-03-30
2 | GitHub Projects kanban board | To Do | Infrastructure |  | High | AI Course | 2026-04-01 | 2026-04-03 | YES
11 | Project folder restructure (data/, notebooks/, reports/, ppt/) | To Do | Infrastructure |  | Medium | Big Data | 2026-04-01 | 2026-04-02 | YES
7 | Deploy to Google Cloud SQL (MySQL) | To Do | Infrastructure |  | High | Big Data | 2026-04-01 | 2026-04-05 | YES
1 | GitHub README (bios, visuals, responsible AI, refs) | To Do | Infrastructure |  | High | AI Course | 2026-04-01 | 2026-04-05 | YES
5 | Research paper citation (<3 yrs, LLM/AI/HR) | To Do | Research + Content |  | Medium | AI Course | 2026-04-01 | 2026-04-05 | YES
6 | Responsible AI section | To Do | Research + Content |  | Medium | AI Course | 2026-04-01 | 2026-04-05 | YES
10 | Ethical reflection | To Do | Research + Content |  | Medium | Big Data | 2026-04-01 | 2026-04-05 | YES
4 | Conference poster layout + template | To Do | Design + Delivery |  | High | AI Course | 2026-04-01 | 2026-04-10 | YES
9 | Big Data slide deck structure | To Do | Design + Delivery |  | High | Big Data | 2026-04-01 | 2026-04-14 | YES
REH | Presentation rehearsal plan | To Do | Design + Delivery |  | Medium | Shared | 2026-04-01 | 2026-04-14 | YES
A4 | Feature engineering on censored PDs | To Do | Technical | Steven | High | Big Data | 2026-04-01 | 2026-04-05 | YES
12 | Pay estimation prompt template | To Do | Technical | Steven | Medium | Shared | 2026-04-01 | 2026-04-05 | YES
A5 | H2O AutoML training | To Do | Technical | Steven | High | Big Data | 2026-04-05 | 2026-04-08
B1 | LangChain multi-agent PoC (Assignment 5) | To Do | Technical | Steven | High | AI Course | 2026-04-09 | 2026-04-11
B2 | skill.md + template files | To Do | Technical | Steven | Medium | AI Course | 2026-04-11 | 2026-04-12
B3 | Design rationale report (1 page) | To Do | Technical | Steven | Medium | AI Course | 2026-04-11 | 2026-04-12
3 | Streamlit web app (agentic AI) | To Do | Technical | Steven | High | AI Course | 2026-04-11 | 2026-04-14
8 | Visualizations (SHAP, PDP, distributions) | To Do | Technical | Steven | High | Big Data | 2026-04-08 | 2026-04-12
13 | Validate against 10+ W&M positions | To Do | All Domains | Everyone | High | Shared | 2026-04-01 | 2026-04-12 | YES
14 | Data dictionary | To Do | All Domains |  | Medium | HR Handoff | 2026-04-14 | 2026-04-18
15 | User guide / SOP | To Do | Research + Content |  | Medium | HR Handoff | 2026-04-14 | 2026-04-18
16 | Validation report | To Do | Technical | Steven | Medium | HR Handoff | 2026-04-14 | 2026-04-18

## Dashboard
Metric | Value
Tasks Done | 17
In Progress | 0
To Do | 22
Blocked | 1
Total | 39
Domain | Task Count
Infrastructure | 4
Research + Content | 4
Design + Delivery | 3
Technical (Steven) | 12
Shared/All | 16
Key Dates
AI Poster | April 15, 2026
Big Data Deck | April 17, 2026
Updated
March 31, 2026